## Release Plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2022-11-07 | 14 | 2022-11-20 | 14 | 15 | Released | 2022-11-20 | Entrega Sprint 3 (Entrega de los datos y Bakend ) | 107.1%
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
3 | 2022-11-07 | 4 | 2022-11-10 | 4 | 5 | Released | 2022-11-20 | Optimización de la aplicación | 40% | 25%
3 | 2022-11-11 | 2 | 2022-11-12 | 2 | 2 | Released | 2022-11-20 | seguridad del entorno | 10% | 0%
3 | 2022-11-13 | 3 | 2022-11-15 | 3 | 3 | Released | 2022-11-20 | Gestionar e integrar la base de datos | 20% | 0%
3 | 2022-11-16 | 2 | 2022-11-17 | 2 | 2 | Released | 2022-11-20 | Elaborar mejoras para las actualizaciones | 10% | 0%
3 | 2022-11-18 | 2 | 2022-11-19 | 2 | 2 | Released | 2022-11-20 | Soluciones de posibles errores que se presenten | 10% | 0%
| 2022-11-20 | 1 | 2022-11-20 | 1 | 1 | Released | 2022-11-20 | Control de calidad del producto | 10% | 0%
Unplanned
Unplanned
Historias no asignadas |  |  |  | 0
Total Size |  |  |  | 14 | 15
|  |  |  | Estimadas | Reales
Formulas:
Start = IF(OR(B14="",[Incr.]=""),"",B14)
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Story Type | Comments | Additional Comments
1 | Datos y Backend | Done | 4 | 3 | 1 | Datos y Backend | Se realiza optimización de la aplicación
2 | Datos y Backend | Done | 2 | 3 | 1 | Datos y Backend | Se realiza validación de seguridad del entorno
3 | Datos y Backend | Done | 2 | 3 | 1 | Datos y Backend | Se realiza gestión de integración de la base de datos
4 | Datos y Backend | Done | 2 | 3 | 1 | Datos y Backend | Se realiza controles de calidad del aplicativo
5 | Datos y Backend | Done | 2 | 3 | 1 | Datos y Backend | Se realiza elaboraciones de mejoras para las actualizaciones
6 | Datos y Backend | Done | 2 | 3 | 1 | Datos y Backend | Soluciones de posibles errores que se presenten
Proyecto
Académica
Académica
Note on C2: ====== ID#AAAAO20iw4E Use the following statuses (2021-09-03 00:19:36) Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D2: ====== ID#AAAAO20iw4I Petri Heiramo (2021-09-03 00:19:36) Story Points or Ideal Days
Note on E2: ====== ID#AAAAO20iw4A Petri Heiramo (2021-09-03 00:19:36) Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F2: ====== ID#AAAAO20iw38 Petri Heiramo (2021-09-03 00:19:36) You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.