## Release Plan
Increment Plan
Incr. | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | % Esfuerzo vs Estimación
1 | 2022-11-21 | 7 | 2022-11-27 | 7 | 7 | Released | 2022-11-27 | Entrega Sprint 4 (Despliegue y distribución) | 100%
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Sprint Plan
Sprint | Start | Days | End | Estimated Size | Real Size | Status | Release Date | Goal | Increment | % Error estimación
4 | 2022-11-21 | 2 | 2022-11-22 | 2 | 2 | Released | 2022-11-22 | Creación de usuario e integración en GitHub para despliegue | 30% | 0%
4 | 2022-11-23 | 2 | 2022-11-24 | 2 | 2 | Released | 2022-11-24 | Despliegue de Frontend y actualización de rutas para conexión | 30% | 0%
4 | 2022-11-25 | 2 | 2022-11-26 | 2 | 2 | Released | 2022-11-27 | Creación beta para la prueba de la aplicación | 30% | 0%
4 | 2022-11-27 | 1 | 2022-11-27 | 1 | 1 | Released | 2022-11-27 | Corrección de errores | 10% | 0%
Historias no asignadas |  |  |  | 0
Total Size |  |  |  | 7 | 7
|  |  |  | Estimadas | Reales
Formulas:
Start = IF(OR(B14="",[Incr.]=""),"",B14)
Start = IF(AND([Start, row above]<>"",[Days, row above]<>"",[Days]<>""),[Start, row above]+[Days, row above],"")
End = IF(OR([Start]="",[Days]=""),"",[Start]+[Days]-1)
End = IF(AND([Start]<>"",[Days]<>""),[Start]+[Days]-1,"")

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | Story Type | Comments | Additional Comments
1 | Despliegue Backend | Done | 2 | 4 | 1 | Despliegue y distribución | Creación de usuario e integración en GitHub para despliegue
2 | Despliegue frontend | Done | 2 | 4 | 1 | Despliegue y distribución | Despliegue de Frontend y actualización de rutas para conexión
3 | Pruebas y funcionamiento | Done | 2 | 4 | 1 | Despliegue y distribución | Creación beta para la prueba de la aplicación
4 | Correciones de errores | Done | 1 | 4 | 1 | Despliegue y distribución | Corrección de errores
Proyecto
Académica
Académica
Note on C2: ====== ID#AAAAO20iw4E Use the following statuses (2021-09-03 00:19:36) Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D2: ====== ID#AAAAO20iw4I Petri Heiramo (2021-09-03 00:19:36) Story Points or Ideal Days
Note on E2: ====== ID#AAAAO20iw4A Petri Heiramo (2021-09-03 00:19:36) Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F2: ====== ID#AAAAO20iw38 Petri Heiramo (2021-09-03 00:19:36) You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.